## About
Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7
Player Class |  | Professor Class
Map Class
The top graph is where we start coding the actual project. Week 1 for this is when we start the project. |  |  | Events Class
Integration of all classes
Design and Ideas for a project | [5 empty] | Touch Ups, and problem fixing
Project Proposal
This second graph is the work we have done starting from the beginning of the semester. |  |  | UML
TimeLine
The first few weeks is when we work on developing our player/professor class. This is one of the major classes and plays a signifigant role in development/testing
The next phase is working with the map and implementing funcitons such as save/load and map manipulation. This will be the true start of testing as we can move a player around a map and change dumby variables.
When we start work on the events class this is when we create what actually happens to the player in the game. Ex: Puzzles, knowledge fights, ect.
The integration of all classes is when we smooth out the handling of each class and how they interact with each other. This will be the time when we do the most testing.
Finally we clean up with problem fixes and attempt to tighten the handling of the game as well as we can.

## Light
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-03-18 |  |  |  |  | March | [13 empty] | April | [34 empty] | May
Scrolling Increment: | 1 | time axis 2021-03-19 to 2021-05-13
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-03-19 to 2021-05-13
TITLE 1
Task 1 | Goal | Name | 25% | 2021-03-18 | 3 | 2021-03-19: 2; 2021-03-20: 2
Task 2 | Milestone |  |  | 2021-03-23 | 1 | bar: 2021-03-23
Task 3 | Low Risk |  | 50% | 2021-03-15 | 10
Task 4 | Milestone |  |  | 2021-04-07 | 1 | bar: 2021-04-07
Task 5 | Med Risk |  | 10% | 2021-03-24 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-03-24 | 13
Task 2 | On Track |  | 50% | 2021-03-26 | 9
Task 3 | Low Risk |  | 33% | 2021-03-31 | 11
Task 4 | Milestone |  |  | 2021-04-02 | 1 | bar: 2021-04-02
Task 5 |  |  |  | 2021-04-03 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-04-02 | 4
Task 2 | Med Risk |  |  | 2021-04-05 | 14
Task 3 | On Track |  |  | 2021-04-20 | 6
Task 4 | Goal |  |  | 2021-04-24 | 3 | 2021-04-24: 2; 2021-04-25: 2; 2021-04-26: 2
Task 5 | Low Risk |  |  | 2021-03-24 | 19
TITLE 4
Task 1 |  |  |  | 2021-04-27 | 15
Task 2 |  |  |  | 2021-05-11 | 5
Task 3 | Milestone |  |  | 2021-06-22 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Dark
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-03-18 |  |  |  |  | March | [13 empty] | April | [34 empty] | May
Scrolling Increment: | 1 | time axis 2021-03-19 to 2021-05-13
Milestone description | Category | Assigned to | Progress | Start | Days | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T
TITLE 1
Task 1 | Goal | Name | 25% | 2021-03-18 | 3 | F: 2; S: 2
Task 2 | Milestone |  |  | 2021-03-23 | 1 | bar: T
Task 3 | Low Risk |  | 50% | 2021-03-15 | 10
Task 4 | Milestone |  |  | 2021-04-07 | 1 | bar: W
Task 5 | Med Risk |  | 10% | 2021-03-24 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-03-24 | 13
Task 2 | On Track |  | 50% | 2021-03-26 | 9
Task 3 | Low Risk |  | 33% | 2021-03-31 | 11
Task 4 | Milestone |  |  | 2021-04-02 | 1 | bar: F
Task 5 |  |  |  | 2021-04-03 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-04-02 | 4
Task 2 | Med Risk |  |  | 2021-04-05 | 14
Task 3 | On Track |  |  | 2021-04-20 | 6
Task 4 | Goal |  |  | 2021-04-24 | 3 | S: 2; S: 2; M: 2
Task 5 | Low Risk |  |  | 2021-03-24 | 19
TITLE 4
Task 1 |  |  |  | 2021-04-27 | 15
Task 2 |  |  |  | 2021-05-11 | 5
Task 3 | Milestone |  |  | 2021-06-22 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one

## Color
PROJECT TITLE
Company name |  |  |  |  | Legend: | On track |  |  |  |  | Low risk |  |  |  |  | Med risk |  |  |  |  | High risk |  |  |  |  | Unassigned
Project lead
Project Start Date: | 2021-03-18 |  |  |  |  | March | [13 empty] | April | [27 empty] | May
Scrolling Increment: | 5 | time axis 2021-03-23 to 2021-05-17
Milestone description | Category | Assigned to | Progress | Start | Days | time axis 2021-03-23 to 2021-05-17
TITLE 1
Task 1 | Goal | Name | 25% | 2021-03-18 | 3
Task 2 | Milestone |  |  | 2021-03-23 | 1 | bar: 2021-03-23
Task 3 | Low Risk |  | 50% | 2021-03-15 | 10
Task 4 | Milestone |  |  | 2021-04-07 | 1 | bar: 2021-04-07
Task 5 | Med Risk |  | 10% | 2021-03-24 | 6
TITLE 2
Task 1 | High Risk |  | 60% | 2021-03-24 | 13
Task 2 | On Track |  | 50% | 2021-03-26 | 9
Task 3 | Low Risk |  | 33% | 2021-03-31 | 11
Task 4 | Milestone |  |  | 2021-04-02 | 1 | bar: 2021-04-02
Task 5 |  |  |  | 2021-04-03 | 24
TITLE 3
Task 1 | On Track |  |  | 2021-04-02 | 4
Task 2 | Med Risk |  |  | 2021-04-05 | 14
Task 3 | On Track |  |  | 2021-04-20 | 6
Task 4 | Goal |  |  | 2021-04-24 | 3 | 2021-04-24: 2; 2021-04-25: 2; 2021-04-26: 2
Task 5 | Low Risk |  |  | 2021-03-24 | 19
TITLE 4
Task 1 |  |  |  | 2021-04-27 | 15
Task 2 |  |  |  | 2021-05-11 | 5
Task 3 | Milestone |  |  | 2021-06-22 | 1
Task 4
Task 5
To add more data, Insert new rows ABOVE this one